# FINTECH 590 Setup Card: Group 2

Oct 6, 2026

- Group 2 is building a backtest ready historical options dataset for S&P 500 stocks. The sources are chosen.

## Sources

| Source | Gives us | Access | Join key | Pulled so far | Owner |
| --- | --- | --- | --- | --- | --- |
| OptionMetrics (WRDS) | Option quotes, volatility surfaces | Yes, verified Oct 6 with a live login: 6 of 6 checked tables open (make access). | secid | Not yet | TBD |
| CRSP (WRDS) | Historical S&P 500 membership, dated stock IDs and corporate actions | Yes, verified Oct 6 with a live login: 4 of 4 checked tables open (make access). | permno and membership date intervals | Not yet: membership intervals and dated symbol links | Loki |
| Broker API | Stock prices, bid/ask quotes and volume | Existing collector; course pilot adaptation pending | Symbol and timestamp; dated permno mapping pending | Recent intraday data collected. Course export and 2004 onward coverage: not yet verified. | Loki |
| Compustat quarterly (WRDS) | Earnings report date, no time of day | Yes, verified Oct 6 with a live login | gvkey | 10 pilot tickers, 2004 to 2025. | Nils |
| I/B/E/S actuals (WRDS) | Earnings announce date and time of day | Yes, verified Oct 6 with a live login | I/B/E/S ticker | 10 pilot tickers | Nils |
| SEC EDGAR | Earnings press releases, filing timestamps | Yes, free and no login. Needs a contact User Agent header, now set. | CIK | Earnings 8K filings (Item 2.02) for 9 of 10 pilot tickers: 773 filings, Oct 2004 to Nov 2025, with acceptance time in Eastern. XOM returned none. | Abhi (filing list), Xueyun (press release text) |
| LLM (press release extraction) | Announcement date and before open or after close, from Exhibit 99.1 | API key needed, cost tracked | EDGAR accession | Not yet, prompt drafted by Oct 21 | Xueyun |
| Bloomberg, LSEG | Spot check validation | Reported available | Ticker, RIC | Not yet | TBD |
| IBKR | Live quotes for the end of semester test | Reported available | Contract ID | Not yet, planned for late in the semester | TBD |

## How the sources fit together

CRSP permno is the hub. Every other ID maps to it through a dated link table, so a reused ticker never silently joins two companies, and every join is made as of a date. Broker symbols will be matched to dated CRSP identifiers and membership on each observation date. Historical membership and the broker symbol-to-permno bridge are not yet built.

| Link | From | To | Link table (names to confirm in the access check) |
| --- | --- | --- | --- |
| OptionMetrics to CRSP | secid | permno | wrdsapps.opcrsphist, with a match score |
| CRSP to Compustat | permno | gvkey | CRSP Compustat Merged link history, with link date ranges |
| CRSP to I/B/E/S | permno | I/B/E/S ticker | wrdsapps.ibcrsphist, with a match score |
| Compustat to EDGAR | gvkey | CIK | Compustat company table |
| Broker stock data to CRSP | Symbol and timestamp | permno and date | Not yet: dated symbol-to-permno mapping required |

## Not yet, and what blocks it

- Table level WRDS check: done Oct 6 by Nils with a live Duo login. OptionMetrics, CRSP, Compustat, I/B/E/S and the link tables all open (see docs/access_report.md). The Compustat and I/B/E/S pilot pulls ran and were compared (see data/processed/earnings/earnings_compare_summary.md).

- Box deposit and licensing: not yet. We do not know if derived OptionMetrics, CRSP, Compustat and I/B/E/S data may go in the course Box folder. Blocked on a question to Alessio.

- Novelty check: not yet. We still need to confirm no finished public dataset exists. OptionMetrics surfaces and ORATS are the closest products.

- Trading cost source: not yet decided. We need to choose where realistic bid and ask spreads come from.

- EDGAR and LLM extraction: owner Xueyun. The earnings 8K filing list is pulled (773 filings, 9 of 10 pilot tickers). Next: download the Exhibit 99.1 press release text for each filing, then prompt an LLM to extract the announcement date and before open or after close, with a fixed JSON output. Validation plan: hand check a random sample of 100 releases and report the agreement rate and error types. Also compare against I/B/E/S times and EDGAR acceptance times. API cost is logged per call. No WRDS needed. Target: demo by Oct 21.

Stocks and membership (Loki): broker pilot export, historical membership pull and dated identifier mapping not yet. Need agreed stocks/date range and live WRDS checks; long-history coverage remains unverified.

- Moving parts & aligning data from different sources

- What worries us is that there are a lot of moving parts to this project. We are gathering data from a lot of different sources and are planning on gluing it together. Despite that, we are confident that we can get it done successfully, as long as the team continues to communicate well.

- What is most likely to be wrong currently is our set of assumptions on how the data will fit together. It is easy to look at schemas and to say that we should be able to join things based on this or that field. Once we pull large datasets that may contain anomalies, we will likely run into issues that will require meticulous problem-solving.

- AI has not caused any major issues so far, luckily. We think AI is currently overstating the simplicity of making all the data from different sources fit together.